## ServiceNow Upgrade
WBS | Name | Notes | Start_Date | Finish_Date | Duration | Assignment | Predecessors
1 | Phase 1 - Read the release notes and plan your upgrade | Phase 1 - Read the release notes and plan your upgrade... | February 7, 2019 8:00 AM | February 12, 2019 5:00 PM | 4 days
1.1 | Review upgrade best practices | Review the upgrade best practices available at https://www.servicenow.com/upgrades The upgrade guide and best practices provides additional context and information that will help ensure a successful upgrade. | February 7, 2019 8:00 AM | February 7, 2019 5:00 PM | 1 day
1.2 | Review release notes | Review the release notes for the target ServiceNow feature release and patch as well as previous feature releases that may have been skipped. For example, if upgrading from Kingston to Madrid, be sure to read the London and Madrid release notes. Personalized release notes are provided as part of the Jumpstart your upgrade program. Release notes can also be found at https://docs.servicenow.com/ For specific upgrade considerations, see Upgrade and migration tasks by application or feature. | February 8, 2019 8:00 AM | February 12, 2019 5:00 PM | 3 days |  | 2
1.3 | Review the supported web browsers to determine browser prerequisites | Review the supported web browsers to determine browser prerequisites. For example, versions and types supported, and additional requirements for new UI versions. Compare these supported browsers to your corporate standard and identify any gaps. | February 7, 2019 8:00 AM | February 7, 2019 5:00 PM | 1 day
2 | Phase 2 - Prepare for the development instance upgrade | Phase 2 - Prepare for the development instance upgrade... | February 13, 2019 8:00 AM | February 18, 2019 5:00 PM | 4 days |  | 1
2.1 | Confirm which ServiceNow instances are in-scope for upgrade. | Confirm which ServiceNow instances are in-scope for upgrade. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.2 | Confirm the instance hosting model | Confirm the instance hosting model. For example, ServiceNow cloud, on-premise, or off-premise. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.3 | Determine new functionality or notable changes that need to be validated after the upgrade. | Based on the reviewed release notes and other release materials, determine new functionality or notable changes that need to be validated after the upgrade. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.4 | Confirm plans to enable or disable features introduced in the new product release. | Confirm plans to enable or disable features introduced in the new product release. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.5 | Create a project plan for cloning, upgrading, and testing. | Create a project plan for cloning, upgrading, and testing. | February 14, 2019 8:00 AM | February 14, 2019 5:00 PM | 1 day |  | 8,7
2.6 | Identify core team of testers, power users, and key stakeholders required to validate functionality in the ServiceNow instances before and after the upgrade. | Identify the core team of testers, power users, and key stakeholders required to validate functionality in the ServiceNow instances before and after the upgrade. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.7 | Confirm any change freeze windows impacting the timing for environment clones or upgrades | Confirm whether there are any change freeze windows impacting the timing for environment clones or upgrades. For example, end quarter. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.8 | Confirm impact of non-production instance upgrade to development and testing | Confirm which of the following situations applies to your ServiceNow non-production instances:... | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.9 | Confirm the availability of other systems required for integration testing (key resources and environments). | Confirm the availability of other systems required for integration testing (key resources and environments). | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.1 | Confirm any restrictions in which ServiceNow instances can be used for integration testing | Confirm whether there are any restrictions in which ServiceNow instances can be used for integration testing. For example, an interfacing system is only set up to access a specific ServiceNow test instance. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.11 | Confirm the testing scope and approach | Confirm the testing scope and approach. | February 15, 2019 8:00 AM | February 15, 2019 5:00 PM | 1 day |  | 10
2.12 | Create a comprehensive test plan including test cases for all core instance functionality and integrations. | Create a comprehensive test plan including test cases for all core instance functionality and integrations. | February 18, 2019 8:00 AM | February 18, 2019 5:00 PM | 1 day |  | 16
2.13 | Confirm the method for tracking any defects identified during testing. | Confirm the method for tracking any defects identified during testing. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.14 | Create a high-level implementation plan | Create a high-level implementation plan that covers:... | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.15 | Confirm any change freeze windows impacting the timing for environment clones or upgrades | Confirm whether there are any change freeze windows impacting the timing for environment clones or upgrades. For example, end quarter. | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.16 | Determine whether existing internal training materials, Knowledge Base articles in the customer instance, or other supporting documentation must be updated to a | Determine whether existing internal training materials, Knowledge Base articles in the customer instance, or other supporting documentation must be updated to align with the upgraded version. For example, changes in functionality or user interface. | February 14, 2019 8:00 AM | February 14, 2019 5:00 PM | 1 day |  | 7,8
2.17 | Optional: Schedule the ServiceNow Configuration Review, which provides recommendations to align the customer configurations with ServiceNow best practices. | Optional: Schedule the ServiceNow Configuration Review, which provides recommendations to align the customer configurations with ServiceNow best practices.... | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.18 | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance | February 13, 2019 8:00 AM | February 13, 2019 5:00 PM | 1 day
2.19 | Create a system clone of your production instance and select your development instance as the Target instance | On your production instance, create a system clone and select your development instance as the Target instance. Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the non-production inst | February 14, 2019 8:00 AM | February 14, 2019 5:00 PM | 1 day |  | 19
3 | Phase 3 - Verify your upgrade configurations and schedule the development instance upgrade in HI | Phase 3 - Verify your upgrade configurations and schedule the development instance upgrade in HI... | February 19, 2019 8:00 AM | February 20, 2019 5:00 PM | 2 days |  | 5
3.1 | Check the configuration of the Upgrade scheduled job to view how often and when it runs | Check the configuration of the Upgrade scheduled job to view how often and when it runs. | February 19, 2019 8:00 AM | February 19, 2019 5:00 PM | 1 day
3.2 | Verify that the Upgrade sys_trigger is set properly for upgrading | Verify that the Upgrade sys_trigger is set properly for upgrading. | February 19, 2019 8:00 AM | February 19, 2019 5:00 PM | 1 day
3.3 | Verify that the Check Upgrade Script sys_trigger is set properly for upgrading | Verify that the Check Upgrade Script sys_trigger is set properly for upgrading. | February 19, 2019 8:00 AM | February 19, 2019 5:00 PM | 1 day
3.4 | If applicable, request a version entitlement. | If applicable, request a version entitlement. | February 19, 2019 8:00 AM | February 19, 2019 5:00 PM | 1 day
3.5 | Schedule the upgrade in HI | Schedule the upgrade in HI. | February 20, 2019 8:00 AM | February 20, 2019 5:00 PM | 1 day |  | 28,26,27
4 | Phase 4 - Upgrade and validate the development instance | Phase 4 - Upgrade and validate the development instance... | February 21, 2019 8:00 AM | February 28, 2019 5:00 PM | 6 days |  | 25
4.1 | DEV: Using the Upgrade Monitor, monitor the upgrade; validate upgrade is complete. | Using the Upgrade Monitor, monitor the upgrade to your instance and validate that the upgrade to your development instance is complete. | February 21, 2019 8:00 AM | February 21, 2019 5:00 PM | 1 day |  | 30,17
4.2 | DEV: Process skipped records list in the Upgrade Monitor. | After the upgrade for your development instance is complete, process the skipped records list in the Upgrade Monitor. | February 22, 2019 8:00 AM | February 26, 2019 5:00 PM | 3 days |  | 32
4.3 | DEV: Identify update sets | Identify your update sets. | February 21, 2019 8:00 AM | February 21, 2019 5:00 PM | 1 day
4.4 | DEV: Before and after upgrading, conduct smoke tests | Before and after upgrading, conduct smoke tests on your development instance. Use your comprehensive test plan to perform functional testing. | February 27, 2019 8:00 AM | February 28, 2019 5:00 PM | 2 days |  | 33,32
5 | Phase 5 - If applicable: Upgrade and validate your other non-production instances, such as your test instance | Phase 5 - If applicable: Upgrade and validate your other non-production instances, such as your test instance... | February 18, 2019 8:00 AM | March 22, 2019 5:00 PM | 25 days |  | 31
5.1 | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance | Notify impacted users and internal stakeholders of the scheduled date/time for cloning (from production) and upgrade of the Sub-Production instance... | March 1, 2019 8:00 AM | March 1, 2019 5:00 PM | 1 day
5.2 | NON-PROD: Create a system clone from Prod and select the applicable NON-PROD instance as the Target instance | On your production instance, create a system clone and select your development instance as the Target instance. | March 1, 2019 8:00 AM | March 1, 2019 5:00 PM | 1 day |  | 35
5.3 | NON-PROD: Before upgrade, run Automated Tests | Before executing the upgrade, Automated tests should be run to establish a baseline of what tests passed/failed prior to an upgrade. ... | February 18, 2019 8:00 AM | February 18, 2019 5:00 PM | 1 day |  | 38
5.4 | NON-PROD: Schedule upgrade in HI and verify upgrade configurations | Schedule the non-production upgrade in HI and verify your upgrade configurations. | March 4, 2019 8:00 AM | March 4, 2019 5:00 PM | 1 day |  | 38,39
5.5 | NON-PROD: Validate that the upgrade is complete. | Validate that the upgrade to your non-production instance is complete. | March 5, 2019 8:00 AM | March 5, 2019 5:00 PM | 1 day |  | 40
5.6 | NON-PROD: Install any optional plugins that were installed on your development instance. | Install any optional plugins that were installed on your development instance. | March 6, 2019 8:00 AM | March 6, 2019 5:00 PM | 1 day |  | 41
5.7 | NON-PROD: Install custom applications and post-upgrade fix scripts | Install any custom applications and post-upgrade fix scripts that you need. | March 7, 2019 8:00 AM | March 7, 2019 5:00 PM | 1 day |  | 42
5.8 | NON-PROD: Install update sets. | Install update sets. | March 8, 2019 8:00 AM | March 8, 2019 5:00 PM | 1 day |  | 43
5.9 | NON-PROD: After upgrade, run Automated Tests | After executing the upgrade, Automated tests should be run again and compared against the pre-upgrade baseline to understand what impact the upgrade may have had on functionality. | February 20, 2019 8:00 AM | February 20, 2019 5:00 PM | 1 day |  | 41,44
5.1 | NON-PROD: Perform functional testing and monitor the performance | Perform functional testing and monitor the performance of your instance. | March 11, 2019 8:00 AM | March 22, 2019 5:00 PM | 10 days |  | 44
6 | Phase 6 - Prepare to upgrade the production instance | Phase 6 - Prepare to upgrade the production instance... | February 27, 2019 8:00 AM | March 26, 2019 5:00 PM | 20 days |  | 36
6.1 | Confirm non-production instance defects have been fixed and validated in update sets. | Confirm sign-off from IT and Business stakeholders that all non-production instance defects have been fixed and validated in update sets. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day |  | 46
6.2 | Confirm the core team of key stakeholders to verify post-upgrade prod functionality | Confirm the core team of key stakeholders required to validate functionality in the ServiceNow instance after the production upgrade. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day |  | 17
6.3 | Confirm coverage for Day 1 support post-upgrade. | Confirm coverage for Day 1 support post-upgrade. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day |  | 17
6.4 | Create a Production Upgrade Implementation Plan | Create a Production Upgrade Implementation Plan that includes all upgrade steps, roles and responsibilities, communication plans, key contacts, support coverage for Day 1, and so forth. | February 27, 2019 8:00 AM | February 27, 2019 5:00 PM | 1 day |  | 48,17
6.5 | Schedule Implementation Plan walkthrough and sign-off | Schedule a walkthrough and sign-off of the Implementation Plan with key stakeholders and the core team. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day |  | 51
6.6 | Submit and obtain approvals for change records | Submit and obtain approvals for change records as required by the organization change process. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day |  | 51
6.7 | Send upgrade communications to key stakeholders and end users for production outage and new features | Send a communication to key stakeholders and end users with details for the production upgrade outage, new features, and so forth. | March 26, 2019 8:00 AM | March 26, 2019 5:00 PM | 1 day |  | 53,52
6.8 | Profile the performance of your instance before upgrading | Profile the performance of your instance before upgrading. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day
6.9 | Use the ServiceNow Performance homepage to document the performance of your instance before the upgrade | Use the ServiceNow Performance homepage to document the performance of your instance before the upgrade. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day
6.1 | On your clone, perform functional testing and monitor the performance of your instance. | On your clone, perform functional testing and monitor the performance of your instance. | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day |  | 51
6.11 | OPTIONAL: Conduct performance and load testing. | OPTIONAL: If there are concerns with system performance, it may beneficial to conduct performance and load testing, to determine any impact areas or remediation steps. (Recommended load testing products are Jmeter and LoadImpact) | March 25, 2019 8:00 AM | March 25, 2019 5:00 PM | 1 day
7 | Phase 7 - Upgrade the production instance | Phase 7 - Upgrade the production instance... | March 27, 2019 8:00 AM | April 2, 2019 5:00 PM | 5 days |  | 47
7.1 | PROD: Schedule the upgrade in HI | Schedule the upgrade in HI. | March 27, 2019 8:00 AM | March 27, 2019 5:00 PM | 1 day |  | 57
7.2 | PROD: If applicable, request a version entitlement | If applicable, request a version entitlement. | March 27, 2019 8:00 AM | March 27, 2019 5:00 PM | 1 day
7.3 | PROD: Monitor the upgrade and validate that the upgrade is complete | Monitor the upgrade to your instance and validate that the upgrade to your production instance is complete. | March 28, 2019 8:00 AM | March 28, 2019 5:00 PM | 1 day |  | 60
7.4 | PROD: Apply update sets and post-upgrade fix scripts | Apply any update sets and post-upgrade fix scripts that you have. | March 29, 2019 8:00 AM | March 29, 2019 5:00 PM | 1 day |  | 62
7.5 | PROD: User acceptance testing (UAT) | Validate and test your instance by conducting user acceptance testing (UAT). Verify with all key stakeholders that the system is performing properly after production upgrade, and key functionality is available. | April 1, 2019 8:00 AM | April 1, 2019 5:00 PM | 1 day |  | 63
7.6 | Schedule a Lessons Learned meeting to discuss and document improvements to incorporate into the next ServiceNow upgrade cycle. | Schedule a Lessons Learned meeting to discuss and document improvements to incorporate into the next ServiceNow upgrade cycle.... | March 27, 2019 8:00 AM | March 27, 2019 5:00 PM | 1 day
7.7 | PROD: Celebrate | Celebrate your new upgrade! | April 2, 2019 8:00 AM | April 2, 2019 5:00 PM | 1 day |  | 64